## Trial Committee
Trial 4 - Committee - Action List |  |  |  |  | PLEASE NOTE - some functions only available when opened in Excel NOT Excel Online! - Use filter options of colums below for better overview - Fields 'Priority' and 'Completion Status' use predefined drop-down lists
Action Lead | Action | Priority | Start Date | Due Date | Responsible | Completion Status | additional notes
ALL | Check agenda of DR1 and comment on necessary changes | High | 20/12/2018 | 10/01/2019 | ALL | In Progress | agenda will be closed on 31/01/2019 latest and send to participants of DR1 asap
do not delete // please insert new line above
Trial Owner | update telco invitation to weekly telcos | High | 20/12/2018 | 07/01/2019 | Konstanze | Done
| send invite to DR1 | Normal | 10/01/2019 | 31/01/2019 | Carsten, Konstanze, Elisa | Pending | list of confirmed participants for logistics planning to Andre
| request for remote connection to DR1, at least for Day1 | Normal | 15/01/2019 | 31/01/2019 | Elisa | In Progress
| review TAP progress | Normal | 21/12/2018 | 31/03/2018 | Veronika, Elisa | In Progress
| discuss budget issue regarding evaluation coordinator | High | 10/01/2018 | 18/01/2018 | Christian | In Progress
do not delete // please insert new line above
Trial Host / End User Coordinator | Share minutes/presentation of practitioner (Dec 13th) meeting on CoW | High | 20/12/2018 | 10/01/2019 | Andre (SRH) | Done
| summarizes expected participants in table of TAP to cross-check against max. capacity from safety officer | Normal | 20/12/2018 | 31/01/2019 | Andre (SRH) | In Progress
| SRH will send dates for practitioner meetings that will take place on Thursday mornings | High | 20/12/2018 | asap | Andre (SRH) | Done
| clarify possible involvement of international organizations based in THG in the Trial | High | 20/12/2018 | 17/01/2019 | Erwin (THG) | In Progress | final decision after meeting on Jan 16th
| discuss feature offer from solutions with practitioners on Dec 13th and decide on features to be trialed | High | 10/12/2018 | 20/12/2018 | Andre, Shahid (SRH) Erwin (THG) | Overdue
do not delete // please insert new line above
Scenario Coordinator | provide revised version of the swimming lanes of the scenario | High | 30/11/2018 | 10/01/2019 | Shahid (SRH) | Done | to be updated after practitioners meeting on dec 13th
| provide storyline | Normal | 30/11/2018 | 31/12/2018 | Shahid (SRH) | Overdue | see TIM minutes
| provide workflow diagram needed for each use case during DR1 together with Test-bed coordinator | Normal | 30/11/2018 | 31/01/2019 | Shahid (SRH) Tinus, Steven (XVR) | Pending | must be ready for play through during DR1 together with TIM practitioners
| Decision needed: Telco with scenario responsible people and Humlog regarding final decision on covering shift regulation / plan as use case in the scenario | Normal | 30/11/2018 | 31/12/2018 | Andre, Shahid (SRH) Solution Provider: Michael (WWU) | Done | see TIM minutes
| include international aspects in scenario | High | 30/11/2018 | 31/12/2018 | Andre, Shahid (SRH) Erwin (THG) | Overdue | see collected options in tabel on CoW, emails from Konstanze & Marcel; final decision on international organization involvement after meeting on Jan 16th ! KPI target is ≥ 5 elements of following options: - Cross-border situation assessment / COP by Member States - Cross-border cooperation by Member States - Cross-border resource and logistics planning by Member States - Active participation (as players) of at least two international organisations - Active involvement of ERCC - Information exchange between ERCC and Member States - Common operational picture at ERCC and Member States - Activation of the Union Civil Protection Mechanism - Explicit reference to relevant EU policies
| Decision on use cases in prediction /response phase and what can we manage during scenario / trial time (how many use cases can be played through in the time of the trial)? | Normal | 30/11/2018 | 31/12/2018 | SRH | Overdue | see TIM minutes
| Provision of detailed script | Normal | 30/11/2018 | 31/03/2019 | Shahid | Pending
| Draft of baseline/innovation line(s) | Normal |  |  | Regis (SRH)
do not delete // please insert new line above
Test-bed Coordinator | check on consortium regarding implementation of the needed Geotiff to GeoJSON converter | Low | 20/12/2018 | 10/01/2019 | Tinus (XVR) Gaby (DLR) | Done | 3Di agreed to make this (in 2nd half Jan 2019)
| provide workflow diagram needed for each use case during DR1 together with Solution coordinator | Normal | 30/11/2018 | 31/01/2019 | Shahid (SRH) Tinus, Steven (XVR) | In Progress | must be ready for play through during DR1 together with TIM practitioners Has been agreed in 15/01/2019 telco that detailed use-cases per AC/CT will be made
| Collect test-cases for each solution (based on AC/CT specific detailed use-cases) | Normal | 01/02/2019 | 15/02/2019 | Tinus, Steven (XVR) Solution providers | Pending | Must be ready before online remote test, in week before DR1
| Provide sequence diagram (data exchange with testbed and /or other solution) per solution | Normal | 30/11/2018 | 15/12/2018 | Tinus, Steven (XVR) Solution providers | Done
| Create network diagram (i.e. which IT hardware is where and connected to what) | Low | 01/03/2019 | 31/03/2019 | Steven (XVR), Andre (SRH) | Pending
| provide integration timeline to solution providers | Normal | 30/11/2018 | 30/11/2018 | Tinus (XVR) | In Progress
| Clearance of Multi-User / multiple instances | Normal | 30/11/2018 | 15/12/2018 | Tinus, Steven (XVR) Solution providers | In Progress | What is technically possible until DR1? Related to sequence diagram
| Involve ITTI in Observer Tool usage in Trial 4 | High | 22/01/2019 | 15/02/2019 | Steven (XVR), Grezegorz (ITTI), Erik (TNO) | Pending
do not delete // please insert new line above
Solution Coordinator | organize telco(s) with solution providers / SRH / Evaluation Coordiantor to exchange latest information / clarify open questions | High | 20/12/2018 | 17/01/2019 | Gunnar (DLR) | Done
| inform solution providers about upcoming dates solutions are involved in together with invitation to follow-up telco and add extra date relevant for XVR (testweek directly before DR1). | High | 20/12/2018 | 10/01/2019 | Gunnar (DLR) | Done
do not delete // please insert new line above
Solution Training Coordinator | review time planning for training provided by SRH | Normal | 20/12/2018 | 14/02/2019 | Ludwig (FRQ) | Pending
do not delete // please insert new line above
Evaluation Coordinator | policy research with regard to flood aspects. | Normal | 20/12/2018 | 31/01/2019 | Cor-Jan (HKV) | In Progress
| discuss the potential involvement of HKV as the Trial 4 Evaluation Coordinator | High | 20/12/2018 | 10/01/2019 | Cor-Jan (HKV), DLR | In Progress | Calculation of efforts by Cor-Jan sent to Marcel; request for telco between CorJan/Christian/Marcel
| finalized research questions ready | High | 20/12/2018 | 10/01/2019 | Regis (SRH) | Overdue
| follow-up telco with solution provider to discuss KPIs for Solution Dimension together to be scheduled together with Solution Coordinator | High | 30/11/2018 | 31/12/2019 | Cor-Jan (HKV), Gunnar/Angela (DLR) | Overdue | in cooperation with solution coordinator. From TIMeeting. First the role of the evaluation coordinator was clarified on 10 January 2019.
| follow-up telco for collecting KPIs for Trial Dimension with Trial Committee | High | 30/11/2018 | 14/12/2018 | Cor-Jan (HKV), Gunnar/Angela (DLR) | Overdue | From TIMeeting. First the role of the evaluation coordinator was clarified on 10 January 2019.
| CM Dimension Session at Practitioner Workshop to collect practitioner input for CM Evaluation / KPIs | Normal | 30/11/2018 | 20/12/2018 | Cor-Jan (HKV), Andre (SRH) | Overdue
| Comparison / alignment with trial 1 + 2 lessons learnt, check standards from Trial 1, check DRIVER+ taxonomy, check ISO 9241-11 (KPIs: efficiency, effectiveness, satisfaction) | Normal | 30/11/2018 | 07/12/2019 | Gunnar, Angela (DLR) | Done | From TIMeeting. New version on CoW WP946.../Coordination/KPI. Send to Adam for suggestions and wording.
| formulate data collection plan /evaluation approaches/metrics | High |  |  |  | Pending | see checklist from UW0
do not delete // please insert new line above
External Cooperation Manager | share the external participant list of Trial 1 and Trial 2 in order to check the possibility to involve them again. | Normal | 20/12/2018 | 10/01/2019 | Anna (ARTTIC) | Done
do not delete // please insert new line above
Media Officer
do not delete // please insert new line above
Trial Supervisor (Director) | discuss personell for role of Trial Director | High | 20/12/2018 | 10/01/2019 | Andre (SRH) Erwin (THG) | Done | Regis Flor
do not delete // please insert new line above
Safety Officer | provide approximation of max. capacity for rooms of Trial facility | Normal | 20/12/2018 | 31/01/2019 | Andre (SRH) | In Progress | see Trial Host
do not delete // please insert new line above
Methodology Validation Conductor
do not delete // please insert new line above
TGM Support | review research questions provided by Regis | High | 20/12/2018 | 10/01/2019 | Adam, Nicky (WWU) | Overdue | phone call scheduled for 18/01/2019
do not delete // please insert new line above
Overall SP Coordinator | ask Marcel to discuss the ERCC involvement options for Trial 4 during the ERCC meeting | Normal | 20/12/2018 | 31/01/2019 | Joanna (SRC) | Done | meeting between Project Lead and ERCC end of Jan; see mail from Marcel: We will of course discuss this with DG ECHO/ERCC in Brussels and update you on this. In addition, I would like to suggest that we may also simulate the ERCC involvement. For instance, we could ask an experienced practitioner from within our network to play the role of the ERCC during the Trial. Although in that case the ERCC themselves is not participating, their role is still included in the Trial scenario enabling us to present results related to the EU-relevance of the Trial.
| end email with details on how to proceed with TAP | Normal | 20/12/2018 | asap | Joanna (SRC) | Done
do not delete // please insert new line above
Review Leader
do not delete // please insert new line above

## Solution Providers
Trial 4 - Solution Providers - Action List
Action Lead | Action | Priority | Start Date | Due Date | Responsible | Completion Status | additional notes
ALL | Draw a list of features/possibilities/data offers to SRH for practitioner workshop on Dec 13th | High | 30/11/2018 | 10/12/2018 |  | Done | Aim: Practitioners should answer what they really want (therefore, SRH will ask practitioners what they would like to have from the solution providers in the scenario within the workshop on 13.12.)
| List all solutions/applications for security authentication | High | 2019-01-14 | 2019-01-17 | Tinus | Done
| Trial 4 external solution repository | High | 2019-01-16 | 2019-01-17 | Tinus | In Progress
| Test-bed topics & naming convention | Normal | 2019-01-16 | 2019-01-28 | Tinus | Pending
| Detail use cases per action center | Normal | 2019-01-16 | 2019-01-28 | Steven | Pending
| Creation of test cases | Normal | 2019-01-16 | 2019-02-11 | Tinus+Steven | Pending
Sim-CI | Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Eelco | In Progress
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Eelco | In Progress
| RD to WGS-84 coordinates conversion | Normal | 2019-01-16 | 2019-02-11 | Eelco | Pending
| Example CAP message to LCMS & CrisisSuite | High | 2019-01-16 | 21/2/2019 | Eelco | Pending
| Use case - enable/disabe data layers | Normal | 2018-11-16 | 2019-02-11 | Eelco | Pending
| Use case - play out prediction | Normal | 2018-11-16 | 2019-02-11 | Eelco | Pending
| Use case - select scenario | Normal | 2018-11-16 | 2019-02-11 | Eelco | Pending
| Use case - create screenshots | Normal | 2018-11-16 | 2019-02-11 | Eelco | Pending | Is not needed if Use case - publish info is completed
| Use case - publish info | Normal | 2018-11-16 | 2019-02-11 | Eelco | Pending
3Di | Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Govert | In Progress
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Govert | In Progress
| Example GeoJSON to all solutions | High | 2019-01-16 | 21/02/2019 | Govert | In Progress
| GeoTIFF - GeoJSON converter | High | 2019-01-16 | 2019-02-21 | Govert | Pending
| Use case - DEM alterations | Normal | 2018-11-16 | 2019-02-11 | Govert | Pending
| Use case - visualize alternatives | Normal | 2018-11-16 | 2019-02-11 | Govert | Pending
| Use case - publish flood map prediction | Normal | 2018-11-16 | 2019-02-11 | Govert | Pending
CrisisSuite (Merlin) | Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Ruud | Done | Using the REST adapter
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Ruud | In Progress | sending messages already implemented; receiving to be implemented
| Use case - display map layers | Normal | 2018-11-16 | 2019-02-11 | Ruud | Pending
| Use case - adding/editing summary/overview | Normal | 2018-11-16 | 2019-02-11 | Ruud | Pending
| Use case - publish map layers | Normal | 2018-11-16 | 2019-02-11 | Ruud | Pending
| Use case - publish summary/overview | Normal | 2018-11-16 | 2019-02-11 | Ruud | Pending
Airborne and Terrestrial Situation Awareness - ZKI (DLR) | Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Ralph | In Progress
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Ralph | In Progress
| Use case - requesting current flood map | Normal | 2018-11-16 | 2019-02-11 | Ralph | Pending
| Use case - requesting damage assessment | Normal | 2018-11-16 | 2019-02-11 | Ralph | Pending
Airborne and Terrestrial Situation Awareness - KeepOperational (DLR) | Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Eric | Done | Using the Java adapter
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Eric | Done
| Use case - adding/manipulating/deleting blockades | Normal | 2018-11-16 | 2019-02-11 | Eric | Pending
| Use case - selecting flood scenario | Normal | 2018-11-16 | 2019-02-11 | Eric | Pending
| Use case - planning routes | Normal | 2018-11-16 | 2019-02-11 | Eric | Pending
| Use case - obtaining accessibility information | Normal | 2018-11-16 | 2019-02-11 | Eric | Pending
HumLog (WWU) | provide overview/example of shift plan from Humlog | High | 30/11/2018 | 12/12/2018 |  | Done
| Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Michael | Done | Using the Java adapter
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Michael | Done
| Use case - alter evacuation objectives | Normal | 2018-01-16 | 2019-02-11 | Michael | Pending
| Use case - provide shift plan | Normal | 2018-01-16 | 2019-02-11 | Michael | Pending
| Use case - assess/update evacuation plan | Normal | 2018-01-16 | 2019-02-11 | Michael | Pending
LCMS (TNO) | Choice of Test-bed adapter to use | Normal | 16/11/2018 | 2019-02-11 | Erik | Done | Using the TypeScript/Node adapter
| Integration with the test-bed | Normal | 2018-11-16 | 2019-02-11 | Erik | In Progress
| Example GeoJSON to CrisisSuite | High | 2019-01-16 | 2019-02-21 | Erik | Pending
| Use case - display map layers | Normal | 2018-11-16 | 2019-02-11 | IFV | Done
| Use case - adding messages | Normal | 2018-11-16 | 2019-02-11 | IFV | Done
| Use case - publish map layers | Normal | 2018-11-16 | 2019-02-11 | Erik | Pending
| Use case - publish summary/overview | Normal | 2018-11-16 | 2019-02-11 | Erik | Pending